## Task Tracker
Task ID | Module / Feature | Task Description | Assigned To | Priority | Status | Start Date | Due Date | Est. Hours | Hours Spent | % Complete | Remarks / Blockers | Last Updated
T-001 | Project Setup & Backend Architecture | Set up Spring Boot Maven project, package structure, application configuration and initial Git/GitHub repository. | Dev Karan | High | Completed | 2026-09-30 | 2026-09-30 | 2.5 | 2.5 | 100 | Initial backend project structure and repository setup completed. | 2026-10-06
T-002 | Entity Layer | Create User, Theatre, Screen, Seat and Movie entity classes with JPA-oriented structure. | Dev Karan | High | Completed | 2026-09-30 | 2026-09-30 | 0.5 | 0.5 | 100 | Core theatre, seat, movie and user entities completed. | 2026-10-06
T-003 | Entity Layer | Create Show, Booking, BookingSeat, Payment and Refund entity classes and establish required relationships. | Surya Prakash | High | Completed | 2026-09-30 | 2026-09-30 | 3 | 3 | 100 | Booking, show, payment and refund entities with relationships completed. | 2026-10-06
T-004 | Enum Layer | Create domain enums for roles, statuses, seat types and movie formats. | Dev Karan | High | Completed | 2026-10-01 | 2026-10-01 | 2.5 | 2.5 | 100 | Required domain enums added for the booking workflow. | 2026-10-06
T-005 | Repository Layer | Create repositories for User, Movie, Theatre, Screen and Seat. | Dev Karan | High | Completed | 2026-10-01 | 2026-10-01 | 1 | 1 | 100 | Core Spring Data repositories completed. | 2026-10-06
T-006 | Repository Layer | Create repositories for Show, Booking, BookingSeat, Payment and Refund. | Surya Prakash | High | Completed | 2026-10-01 | 2026-10-01 | 2.5 | 2.5 | 100 | Booking and transaction-related repositories completed. | 2026-10-06
T-007 | DAO Layer | Create DAO classes and data-access flow for core theatre, screen, seat, movie and user modules. | Dev Karan | High | Completed | 2026-10-02 | 2026-10-02 | 3 | 3 | 100 | Core DAO/data-access flow completed. | 2026-10-06
T-008 | DAO Layer | Create DAO classes and data-access flow for show, booking, payment and refund modules. | Surya Prakash | High | Completed | 2026-10-02 | 2026-10-02 | 3 | 3 | 100 | Booking and transaction DAO flow completed. | 2026-10-06
T-009 | DTO Request Layer | Create request DTOs for authentication, users, movies, theatres, screens, seats and shows. | Dev Karan | High | Completed | 2026-10-02 | 2026-10-02 | 0.5 | 0.5 | 100 | Request-side DTO structure completed. | 2026-10-06
T-010 | DTO Request/Response Layer | Create booking, seat-lock, payment, cancellation, refund and response DTOs. | Surya Prakash | High | Completed | 2026-10-03 | 2026-10-03 | 3 | 3 | 100 | Booking, seat-lock, payment and refund DTOs completed. | 2026-10-06
T-011 | Mapper Layer | Create User, Movie, Theatre, Screen and Seat mapper classes for entity-to-DTO conversion. | Dev Karan | High | Completed | 2026-10-03 | 2026-10-03 | 1.5 | 1.5 | 100 | Core entity-to-DTO mappers completed. | 2026-10-06
T-012 | Mapper Layer | Create Show, Booking, Payment and Refund mapper classes and complete DTO conversion flow. | Surya Prakash | High | Completed | 2026-10-01 | 2026-10-01 | 1 | 1 | 100 | Booking and transaction mapper flow completed. | 2026-10-06
T-013 | Service Layer | Define service interfaces for authentication, user, movie, theatre, screen and seat modules. | Dev Karan | High | Completed | 2026-10-03 | 2026-10-03 | 0.5 | 0.5 | 100 | Core service contracts created. | 2026-10-06
T-014 | Service Layer | Define service interfaces for show, booking, seat lock, payment, refund, ticket, QR, notification and reporting modules. | Surya Prakash | High | Completed | 2026-10-02 | 2026-10-02 | 0.5 | 0.5 | 100 | Service contracts for booking and supporting modules completed. | 2026-10-06
T-015 | Service Implementation | Implement authentication, user, movie, theatre, screen and seat business logic. | Dev Karan | High | Completed | 2026-10-04 | 2026-10-04 | 3.5 | 3.5 | 100 | Core backend business logic implemented. | 2026-10-06
T-016 | Service Implementation | Implement show, booking, ticket, refund and related booking workflow logic. | Surya Prakash | High | Completed | 2026-10-04 | 2026-10-04 | 3.5 | 3.5 | 100 | Show, booking, ticket and refund workflow implemented. | 2026-10-06
T-017 | Controller Layer | Implement authentication, user, movie, theatre, screen, seat and show REST controllers. | Dev Karan | High | Completed | 2026-10-05 | 2026-10-05 | 3.5 | 3.5 | 100 | Core REST APIs completed. | 2026-10-06
T-018 | Controller Layer | Implement booking, ticket, payment/refund and administrative REST controller flows. | Surya Prakash | High | Completed | 2026-10-05 | 2026-10-05 | 3.5 | 3.5 | 100 | Booking, ticket, payment/refund and admin APIs completed. | 2026-10-06
T-019 | Exception & Validation | Implement application exceptions, global exception handling, BookingValidator, SeatValidator and PaymentValidator. | Dev Karan | High | Completed | 2026-10-03 | 2026-10-03 | 1 | 1 | 100 | Validation and centralized exception handling completed. | 2026-10-06
T-020 | Integration & Configuration | Configure CORS, Redis, OpenAPI/Swagger and payment/notification integration structure. | Surya Prakash | High | Completed | 2026-10-06 | 2026-10-06 | 3 | 3 | 100 | Backend configuration and integration components completed. | 2026-10-06
T-021 | Seat Locking Support | Implement temporary seat locking and lock-expiry handling using Redis/scheduler support. | Dev Karan | High | Completed | 2026-10-06 | 2026-10-06 | 2.5 | 2.5 | 100 | Temporary seat lock and expiry handling completed. | 2026-10-06
T-022 | Backend Integration & Review | Integrate backend layers, review APIs and resolve issues across completed backend modules. | Surya Prakash | High | Completed | 2026-10-06 | 2026-10-06 | 0.5 | 0.5 | 100 | Final backend API integration review completed. | 2026-10-06
T-023 | React Frontend Setup | Set up React frontend structure, routing and reusable UI foundation. | Hariharan | High | Completed | 2026-10-02 | 2026-10-02 | 3 | 3 | 100 | React foundation and routing completed. | 2026-10-06
T-024 | React Movie & Show UI | Develop movie listing/details, theatre, show and seat-selection screens. | Hariharan | High | Completed | 2026-10-03 | 2026-10-03 | 3 | 3 | 100 | Movie, theatre, show and seat-selection UI completed. | 2026-10-06
T-025 | React Booking & User UI | Develop login/user, booking, booking history, ticket and user-facing screens. | Manish Kumar | High | Completed | 2026-10-04 | 2026-10-04 | 3 | 3 | 100 | User login, booking, history and ticket UI completed. | 2026-10-06
T-026 | React Admin UI | Develop admin-facing screens for theatres, movies, shows, bookings and management flows. | Manish Kumar | High | Completed | 2026-10-05 | 2026-10-05 | 3 | 3 | 100 | Admin-facing management screens completed. | 2026-10-06
T-027 | Frontend API Integration | Connect frontend screens with backend APIs and handle booking/user data flow. | Hariharan | High | Completed | 2026-10-05 | 2026-10-05 | 0.5 | 0.5 | 100 | Frontend-backend API connection completed. | 2026-10-06
T-028 | Frontend Integration & Testing | Run frontend integration checks, fix UI/API issues and verify end-to-end booking screens. | Hariharan | High | Completed | 2026-10-06 | 2026-10-06 | 2.5 | 2.5 | 100 | End-to-end frontend booking flow verified. | 2026-10-06
T-029 | Frontend Integration & Testing | Fix remaining user/admin UI issues and validate payment, ticket and booking-history flows. | Manish Kumar | High | Completed | 2026-10-06 | 2026-10-06 | 3 | 3 | 100 | Final user/admin UI and booking-flow checks completed. | 2026-10-06

## Team Summary
Team Member | Primary Area | Tasks | Total Hours | Relative Workload
Dev Karan | Backend – core modules, APIs, validation & seat locking | 12 | 22.5 | Higher
Surya Prakash | Backend – booking, payment, refund, integration & APIs | 10 | 25.5 | Higher
Hariharan | Frontend – React setup, movie/show/seat UI & integration | 4 | 9 | Standard
Manish Kumar | Frontend – user/admin UI & final frontend validation | 3 | 9 | Standard